Event Planning Guide

With anticipated date for Event late May/early June

JANUARY
- Pencil in date and time based on Organization’s overall events, fundraising, and communications calendar
  - Map out event marketing and communications plan, including press outreach

FEBRUARY
- Assemble Event planning team
  - Assign Event team tasks
- Secure location
- Begin outreach for donations
  - Establish goal for number of donations for the event
- Begin developing marketing materials
- Develop press outreach plan and begin drafting pitch and media kit
- Continue donations outreach and any other collaborations

MARCH
- Save-the-date released (two months before event)
- Event planning team check-in
  - Review donations and any pick-up/storage logistics
  - Begin developing run-of-show for event
  - Begin updating donation information
APRIL
- Begin marketing/promotions via eBlast and social media (six weeks before event)
- Begin creating signage for event
- Organization Board activated to invite their networks (four weeks before event)
- Community marketing/posters

MAY
- Event planning team final check-in (ideally 2 weeks out)
  - Review donations and pick-up/storage logistics
  - Finalize developing run-of-show and supplies + pack list for event
  - Confirm assignments and email volunteers as needed
  - Coordinate all final donation pick-ups and update in tracker
  - Confirm load-in/load-out time and necessary details with venue
- Print and gather all day-of materials and collateral

POST-Event REMINDERS
- Event planning team shares feedback
- Share Event photos and content for post-event coverage
- Thank-you’s to donors, venue, volunteers, other collaborators